## Sheet1
Cluster calibration sprint plan
Days | M | [6 empty] | M
Date | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Camera | [5 empty] | HOLIDAY
| Static camera (pick and drop basket calib) | [6 empty] | Object detection and analysis (Basket empty status, pick and drop)
|  |  | Gripper camera (pick and drop calibration) |  |  |  |  | Gripper camera (Scanner calibration)
Robot
Refactoring (cmake, Remove Qt(just c++ lib))
[8 empty] | Migration to c++lib for pick and drop basket |  | Gripper based calibration at scanner
| TCP communication (cluster calib, Qt c++) |  | Drop basket integration | Pick Basket Integration
Full stack